Lifecycle and Risk-Based Optimization Framework for Condition-Triggered Maintenance of Flexible Pavement Networks under Indian Traffic and Climatic Conditions

Deepak Baskandi

Border Roads Organisation, Email: baskideepak@gmail.com

Abstract

According to the experience in India, the highway agencies are used to following common resurfacing timelines regardless of the real pavement conditions, which can result in the inefficient use of the resources, as well as delays in the required structural repairs. This paper presents a model of maximizing the life cycle of Indian flexible pavement networks, which are activated by conditions and risk weighted. The framework includes the assessment of the pavement condition, the modelling of deterioration, specifically adapted to the climate of tropical monsoons, the probabilistic modelling of structural failure, life-cycle cost analysis, and constrained optimization. The State Highway of 48 kilometres, two lanes around Chennai, Tamil Nadu, was observed in a period of 20 years. Statistical validation was done through Monte Carlo simulation. The streamlined solution led to 18% reduction in discounted life cycle cost; 26 percent add to the duration of serviceable network and 45 percent decrease of major strengthening interventions than in traditional periodic resurfacing. This framework helps change the age-based resurfacing to the performance-based pavement asset management that is consistent with the contemporary Pavement Management Systems. This paper integrated the Indian Roads Congress assessment techniques with lifecycle economics and probabilistic risk modelling into an overall network optimization model.

Keywords: Pavement Management Systems (PMS); Lifecycle Cost Analysis (LCCA); Risk-based Asset Management; Flexible Pavement Deterioration and Condition-Triggered Maintenance.

- Introduction.

  - Background and Context

India has one of the largest and most diverse road networks in the world, encompassing national highways, state highways, district roads, and strategically significant corridors that traverse mountainous, coastal, arid, and high-rainfall regions. Over the past two decades, substantial investments have been directed toward capacity augmentation and geometric improvements; however, the sustainability of these investments increasingly depends on scientifically optimized maintenance planning. Traditionally, pavement maintenance across many Indian agencies has been guided by fixed periodic resurfacing cycles, typically ranging from five to six years, irrespective of the actual structural and functional conditions of the pavement. Although administratively convenient, this approach does not adequately reflect the heterogeneous deterioration patterns induced by varying traffic intensities, axle load spectra, subgrade characteristics, and climatic exposure.

The Indian Roads Congress has developed comprehensive guidelines for the structural evaluation, overlay design, and maintenance of flexible pavements (IRC:82, IRC:115, IRC:37). However, these standards predominantly outline evaluation procedures and design methodologies rather than offering network-level optimization frameworks that connect measurable condition indices to economically optimal intervention timing.

  - Limitations of Uniform Resurfacing Practices

India has one of the largest road networks in the world, exceeding 6.3 million kilometer and encompassing National Highways, State Highways, and district roads (MoRTH 2022). Substantial capital investments over the past two decades have focused on capacity augmentation and geometric upgrades. However, the long-term serviceability of these assets increasingly depends on optimized maintenance programming.

Traditionally, flexible pavement resurfacing in India follows periodic cycles of approximately five years, often independent of measured structural or functional conditions. Although such practices provide administrative simplicity, they fail to account for nonlinear deterioration governed by cumulative equivalent standard axle loads (ESALs), subgrade variability, moisture ingress, and climatic heterogeneity (Haas et al. 1994; Paterson 1987).

The Indian Roads Congress has issued comprehensive guidelines for pavement design and evaluation, including IRC:37 (flexible pavement design), IRC:82 (maintenance of bituminous pavements), and IRC:115 (structural evaluation using deflection methods) (IRC 2018; IRC 2015; IRC 2014). While technically robust at the project level, these standards do not prescribe an integrated network-level optimization framework linking measurable condition indices to economically optimal intervention timing under budgetary constraints.

Globally, lifecycle-optimized pavement management strategies incorporated into the Highway Development and Management Model (HDM-4), a system developed by the World Bank, illustrate that implementing preventive measures at the right time can greatly decrease overall costs for both agencies and users (Kerali et al. 2000; Paterson 1987). Similarly, the Transportation Research Board provides guidance that highlights the importance of asset management based on conditions and informed by risk (Transportation Research Board 2010).

- Research Problem

Indian highway agencies predominantly follow fixed time-based resurfacing cycles that inadequately reflect the actual pavement condition, structural reliability, and lifecycle economics under heterogeneous traffic and climatic environments. The Existing Indian Roads Congress guidelines lack an integrated network-level optimization mechanism. This study addresses the need for a condition-triggered, risk-informed lifecycle framework that optimizes maintenance timing, minimizes long-term costs, and improves the serviceability of flexible pavement networks within realistic budget constraints.

- Review of Standards and Existing Frameworks

3.1	Indian Standards

The regulatory and technical foundations for pavement design and maintenance in India are established through guidelines issued by the Indian Roads Congress (IRC). Among these, IRC:37 provides mechanistic–empirical procedures for the design of flexible pavements based on cumulative equivalent standard axle loads (ESAL), material characterization, and fatigue and rutting criteria (IRC 2018). Although IRC:37 establishes the structural design methodology and principles for determining overlay thickness, its primary focus is on new pavement design and project-level strengthening rather than network-level optimization (Haas et al. 1994; Shahin 2005).

IRC:82 outlines maintenance strategies for bituminous pavements and categorizes interventions into routine, preventive, and periodic renewals. The document identifies distress manifestations and recommends appropriate treatments; however, it does not prescribe calibrated threshold values linked to life-cycle cost optimization or risk-based prioritization. Maintenance timing is largely experience-driven or administratively scheduled (IRC, 2015; OECD, 2001).

IRC:115 provides guidelines for the structural evaluation of flexible pavements using Benkelman Beam Deflection (BBD) and Falling Weight Deflectometer (FWD) data. It establishes procedures for back-calculation, characteristic deflection determination, and overlay design (IRC, 2014). Although technically robust at the section level, IRC:115 does not integrate deflection-based structural adequacy into a dynamic multi-year programming framework (Paterson, 1987; Uddin et al., 2013).

Although IRC standards offer reliable tools for engineering design and assessment, they lack a cohesive, condition-based optimization framework for planning maintenance at the network level (Transportation Research Board 2010).

3.2.	Pavement Management Systems (PMS) in India

Several central and state highway agencies have adopted Pavement Management Systems to facilitate data-driven decision-making (Haas et al. 1994; Shahin 2005). PMS implementations typically incorporate the following:

- Condition surveys (IRI, cracking, rut depth),

- Performance prediction models,

- Treatment libraries,

- Budget-constrained prioritization modules (Uddin et al. 2013; IRC 2015).

In India, many operational Pavement Management Systems (PMS) primarily focus on ranking sections using composite condition indices. Decisions regarding overlays are often based on surface distress thresholds and lack explicit validation of structural capacity. Additionally, deterioration models are frequently borrowed from international datasets without thorough calibration to account for Indian traffic loads, overloading prevalence, and climatic variations (Paterson 1987; Prozzi and Madanat 2000).

The absence of systematically calibrated preventive windows reduces the effectiveness of PMS outputs, particularly in distinguishing between functional and structural triggers for intervention (Labi et al. 2005, TRB 2010).

  - International Asset Management Frameworks

Internationally, the management of pavement assets has shifted towards frameworks that focus on performance and optimize the life cycle. The Highway Development and Management Model (HDM-4), created with support from the World Bank, combines deterioration models, estimates of vehicle operating costs, user delay expenses, and economic assessments to identify the best timing for interventions (Kerali et al. 2000; Odoki and Kerali 2000). The HDM-4 clearly illustrates that implementing preventive maintenance early results in lower net present costs than postponing rehabilitation efforts (Paterson 1987).

Similarly, guidelines from the Federal Highway Administration (FHWA) and the American Association of State Highway and Transportation Officials (AASHTO) emphasize condition-based maintenance triggers, performance modelling, and asset preservation philosophies. These frameworks integrate structural adequacy, functional performance, and lifecycle economics into multi-year optimization algorithms (FHWA 2016; AASHTO 2011).

A notable advancement in international practice is the incorporation of risk-based asset management, wherein failure probability, traffic criticality, and resilience considerations influence prioritization decisions (OECD 2001; Cambridge Systematics 2006). Such approaches extend beyond deterministic condition thresholds and embed uncertainties into maintenance programming.

  - Identified Limitations in Existing Frameworks

Despite the availability of established standards and analytical tools, several limitations are observed when contextualized for Indian highway networks.

    - Fragmented Integration: Structural evaluation (IRC:115), overlay design (IRC:37), and maintenance categorization (IRC:82) operate largely as independent procedures without algorithmic integration into a lifecycle optimization model (Haas et al. 1994).

    - Limited Calibration to Indian Field Conditions: Long-term Indian performance datasets, categorized by climate and traffic class, seldom serve as the basis for deriving the deterioration coefficients and intervention thresholds.

    - Inadequate Risk Quantification:  Current frameworks emphasize economic efficiency but insufficiently account for corridor criticality, climate-induced vulnerability, or probabilistic failure progression (TRB 2010; Markow and Hyman 2009).

    - Administrative Overlay Cycles:  In practice, the frequency of resurfacing is often determined by funding schedules or the importance of the roadnetworkr, rather than by specific condition categories (OECD 2001; Labi et al. 2005).

  - Key Takeaways

The review highlights that although Indian standards offer technically robust design and evaluation methods, and international frameworks provide tools for life cycle optimization, there is a lack of contextualized integration of these components. Specifically, there is a requirement for

- Condition thresholds empirically calibrated for Indian traffic and climate conditions,

- Explicit incorporation of structural adequacy into network-level planning,

- Embedding lifecycle cost minimization within budgetary limits,

- Risk-weighted prioritization of essential corridors.

This study aims to address this gap by combining IRC-compliant evaluation methods with lifecycle economics and probabilistic risk assessment into a comprehensive optimization framework tailored for Indian highway agencies (Uddin et al. 2013, TRB 2010).

- Conceptual Framework of Lifecycle and Risk-Based Optimization

  - Framework Overview

The framework integrates condition-based maintenance triggers, lifecycle cost minimization, and probabilistic risk assessment into a unified optimization architecture for flexible pavement network. It synthesizes structural evaluation procedures compliant with Indian Roads Congress standards, HDM-4 performance modelling principles developed under the World Bank, and risk-informed asset management concepts adopted in infrastructure governance (Kerali et al. 2000; Uddin et al. 2013; Transportation Research Board 2010).

The framework shifts from age-driven resurfacing cycles to state-dependent intervention policies, where treatment timing and type depend on measurable functional and structural condition indicators (Haas et al. 1994; Shahin, 2005).

  - Pavement Condition Assessment

Each pavement section iat time tis represented by a condition vector:

Ci,t={IRIi,t,RDi,t,CRi,t,Di,t}

Where:

- IRI= International Roughness Index

- RD= Rut depth

- CR= Cracking area percentage

- D= Structural deflection indicator

Condition states are categorized into discrete bands (Good, Preventive, Corrective, Structural Distress) based on calibrated thresholds.

  - Deterioration Modelling Layer

Pavement deterioration is treated as a nonlinear time-dependent process influenced by cumulative loading and environmental exposure.

The general transition function is expressed as follows:

Ci,t+1=f(Ci,t,ESALi,t,Climatei)+ϵ

Where:

- f(⋅)is a calibrated deterioration function,

- ϵrepresents stochastic variability.

The treatment application modifies the state as follows:

Ci,t+1post=gk(Ci,t)

where gk(⋅)represents treatment effectiveness (e.g., roughness reset, rut reduction, crack sealing impact).

  - Economic Evaluation Layer

The lifecycle economic objective is to minimize the Net Present Cost (NPC) over planning horizon T:

NPC=t=0T11r)tikxi,tk⋅Costk+UserCosti,t

Where:

- r= discount rate,

- xi,tk= binary decision variable for treatment k,

- Costk= agency cost of treatment,

- UserCosti,t= vehicle operating and delay costs (optional inclusion).

Preventive maintenance applied during the early deterioration stages reduces long-term expenditure escalation by moderating performance decline slopes, consistent with the lifecycle preservation theory (Haas et al. 1994). Therefore, the economic layer identifies the intervention year that minimizes the cumulative discounted expenditure.

  - Risk-Weighted Prioritisation and Optimisation

Engineering conditions alone do not capture strategic or operational criticality. Therefore, risk is quantified as

Riski,t=Pfail,i,t×Consequencei

The failure probability is estimated using logistic regression models widely applied in infrastructure reliability analysis (Morcous 2006):

Pfail,i,t=11+e-(a+bCi,t+cESALi,t)

Consequence weighting may include:

- Traffic volume (AADT),

- Freight intensity,

- Corridor criticality,

- Climate vulnerability index.

Under the traditional policy, the intervention year is predefined (e.g., 5-year cycle). The proposed framework is as follows:

tintervention=arg⁡min⁡t(NPC+λRisk)

Subject to:

∑Costi,t≤Bt

where:

- λ= risk-aversion parameter

- Bt = represents available budget in year t.

Intervention timing is endogenous and condition-driven. This ensures that high-risk corridors receive priority under budget constraints. Risk-constrained optimization approaches are aligned with network-level pavement management methodologies (Fwa 2005; Zhang and Durango-Cohen 2013).

  - Treatment Eligibility Constraints

Treatment application is restricted by the following condition thresholds:

Clower,k≤Ci,t≤Cupper,k

Structural overlay becomes mandatory if:

Di,t>Dthreshold

Minimum serviceability requirement:

IRIi,t≤IRImax

Optional network-level constraints:

Length in Good ConditionTotal Network Length≥α

Where α is policy-defined target.

  - Integration into PMS Workflow

The framework is designed to integrate seamlessly into current PMS settings. The operational process includes the following steps.

- Import data from condition surveys and structural assessments.

- The network is divided into uniform segments.

- Deterioration models are calibrated.

- A threshold-treatment eligibility matrix was implemented.

- Conduct multiperiod optimization within the limits of annual budgets.

- A prioritized intervention plan was developed.

The system functions repetitively, annually updating the condition states based on the treatments applied and the deterioration observed. This structure enables IRC-compliant structural evaluations within a network-level optimization framework.

  - Theoretical Basis

The framework is based on three theoretical pillars:

    - Lifecycle Cost Theory:  Based in infrastructure economics, lifecycle theory minimizes total discounted cost over asset life (Hall et al. 2003). Early intervention is justified when the marginal cost of delay exceeds the treatment cost.

    - Reliability and Survival Theory:  Pavement deterioration is treated as a probabilistic process (Madanat et al. 1995). Logistic and hazard-based models estimate the time-to-failure distribution, enabling risk-informed decision-making.

    - Multi-Criteria Optimization Theory: The decision problem is formulated as a constrained optimization that integrates cost minimization and risk mitigation. Solutions use dynamic programming, mixed-integer linear programming (MILP), or heuristic algorithms based on the network scale.

  - Conceptual Transition

The framework represents a paradigm shift from:

- Age-driven resurfacing to State-dependent optimization

- Deterministic ranking to Probabilistic risk weighting

- Project-level design to Network-level lifecycle programming

It provides a mathematically defensible and operationally implementable pathway for transitioning Indian highway maintenance practices toward data-driven, economically optimized, and risk-informed asset management (Transportation Research Board 2010; Uddin et al. 2013).

- Case Study: Two-Lane Bituminous State Highway Near Chennai, Tamil Nadu

  - Introduction to Study Corridor

To demonstrate the real-world application of the proposed lifecycle and risk-based optimization framework, a detailed analysis was conducted on a two-lane bituminous State Highway corridor situated in the peri-urban area of Chennai, Tamil Nadu. This corridor is characterized by a high volume of commercial traffic owing to its proximity to industrial zones and logistics activities associated with the Chennai Port.

The study section exemplifies medium-to-high-traffic two-lane flexible pavements typically managed by State Public Works Departments in southern India.

  - Key Corridor Characteristics

Location: Chennai-Vandalur corridor

Length: 48 km

Carriageway: Two-lane undivided

Width: 7.0 m

Shoulders: Partially paved

Pavement Composition: Bituminous Concrete (BC) over Dense Bituminous Macadam (DBM)

Last Overlay: 2017

Subgrade: Clayey soil (CBR 7-9%)

Terrain: Rolling

Climatic conditions:

- Tropical wet and dry climate

- Annual rainfall: 1000-1200 mm

- Heavy northeast monsoon influence

- Pronounced moisture susceptibility

These environmental conditions accelerate stripping, rutting, and subgrade weakening processes.

  - Traffic Loading

Comprehensive traffic surveys were conducted during 2023-2024 (Table 1)

Table 1: Traffic characteristics obtained from traffic surveys

| Parameter | Observed Value |
| --- | --- |
| AADT | 27,400 vehicles/day |
| Commercial Vehicles | 45% |
| Annual Growth Rate | 6.2% |
| Estimated Cumulative Traffic (20 years) | 45-53 MSA |
| Overloading Index | ~20% |

The relatively high freight component renders structural evaluation critical for maintenance planning.

  - Baseline Pavement Condition Assessment (2024)

The 48 km corridor was divided into 64 homogeneous sections (average length of approximately 750 m).

    - Functional Indicators

Table 2: Survey results of various functional indicators

| Indicator | Mean | Range |
| --- | --- | --- |
| IRI | 3.85 m/km | 2.2-5.6 |
| Rut Depth | 13.8 mm | 4-21 |
| Cracking | 21% | 6-36 |

    - Condition Distribution

Table 3: Pavement condition assessment

| Condition Band | IRI (m/km) | Network Share |
| --- | --- | --- |
| Good | <2.5 | 12% |
| Preventive | 2.5-3.5 | 24% |
| Corrective | 3.5-4.5 | 38% |
| Structural Distress | >4.5 | 26% |

Nearly one-fourth of the corridor had already entered the structural distress phase, indicating a delayed intervention.

  - Structural Evaluation

- Deflection measurements were performed in accordance with the IRC:115 provisions.

- The characteristic deflection values ranged from 0.88 mm to 1.57 mm.

- The IRC overlay trigger deflection for this traffic category (~45 MSA) was approximately 1.0 mm.

- Sections that exceeded the structural threshold constituted 28% of the network.

- This confirms that deterioration is not purely functional but is also structurally significant.

  - Deterioration Modelling for Coastal Tamil Nadu Conditions

Regression-based deterioration modelling was performed to reflect monsoon-driven moisture effects.

IRIt+1=0.83⋅IRIt+0.020⋅ESAL+0.0031⋅Rainmonsoon

Model statistics:

- R² = 0.79

- Mean Absolute Percentage Error (MAPE) = 10.8%

- Statistical significance (p < 0.01)

The rainfall coefficient was statistically significant, highlighting the climatic influence on the progression of deterioration.

  - Maintenance Strategy Scenario

- A 20-year planning horizon (2025-2045) was adopted.

- Discount rate: 10%

- Annual budget constraint: ₹ 9.0 crore

    - Scenario A: Periodic Resurfacing

- 40 mm BC overlay after every 5-year intervals

- No differentiation based on condition

    - Scenario B: Condition-Triggered Maintenance

- Preventive micro-surfacing (IRI 2.5-3.5)

- Overlay (IRI 3.5-4.5)

- Structural strengthening where deflection exceeds IRC threshold

    - Scenario C: Risk-Weighted Optimization

Prioritization was based on the following

Risk=Pfailure×(AADT×Freight×Connectivity)

Connectivity weighting was introduced due to peri-urban socioeconomic significance.

  - Lifecycle Cost Results

Table 4: Total Discounted Lifecycle Cost (20 Years)

| Scenario | Total Cost (₹ Crore) | Relative (%) |
| --- | --- | --- |
| A | 248 | 100% |
| B | 212 | 86% |
| C | 202 | 82% |

The optimized framework achieved an 18% lifecycle cost reduction compared with periodic resurfacing.

  - Network Performance Comparison

    - Mean IRI Over Time

Table 5: Mean IRI Progression over Analysis Period for Maintenance Scenarios

| Year | Scenario A | Scenario C |
| --- | --- | --- |
| 2025 | 3.85 | 3.85 |
| 2030 | 4.31 | 3.46 |
| 2035 | 3.92 | 3.18 |
| 2040 | 4.45 | 3.49 |
| 2045 | 3.98 | 3.27 |

Scenario C consistently maintained a lower mean roughness.

    - Condition Distribution at Year 2045

Table 6: Long-Term Network Serviceability Distribution under Scenario A and Scenario C

| Condition Band | Scenario A | Scenario C |
| --- | --- | --- |
| Good/Fair | 48% | 74% |
| Corrective | 30% | 18% |
| Structural Distress | 22% | 8% |

The serviceable network proportion increased by 26% under the optimized scheduling.

  - Structural Rehabilitation Frequency

Table 7: Structural Strengthening Intervention Frequency across Scenarios A and Scenario C

| Metric | Scenario A | Scenario C |
| --- | --- | --- |
| Major Strengthening Events | 11 | 6 |
| Average Deferral | - | + 3.6 years |

Risk-weighted scheduling reduces premature strengthening and spreads expenditures more evenly.

  - Sensitivity and Robustness Analysis

Monte Carlo simulation (1,000 iterations) incorporating traffic growth (±1.2%), rainfall variability (±8%), and treatment effectiveness uncertainty (±7%) yielded:

- Mean lifecycle savings: 17.6%

- Standard deviation: 3.1%

- Probability of outperforming periodic resurfacing: 93%

Under a 20% reduced annual budget Scenario A (~₹ 7.2 crore/year), structural distress reached 31% by year 20 under the periodic strategy (Scenario A) but remained limited to 15% under the optimized framework (Scenario C). Thus, the optimized scheduling demonstrates robustness under fiscal limitations typical of state-level agencies.

  - Policy and Operational Implications

- Personalizing preventative thresholds to consider the impact of coastal monsoons on lifecycle efficiency.

- The introduction of deflection-based structural requirements (IRC:115) prevents premature overlays to minimize the costs in the long run.

- The high impact areas can be prioritized to get the first intervention by risk weighting the traffic and the connectivity indices even with limited budgets.

- A smoothed budget enhances the practicality of execution and eliminates the annual expenditure variability.

- These measures only need a few structural adjustments that can be incorporated into the existing PMS models but provide substantial efficiency gains.

  - Case Study Summary

For a representative two-lane bituminous road near Chennai:

- Lifecycle cost reduced by approximately 18%

- Serviceable network length improved by 26%

- Structural rehabilitation frequency reduced by 45%

- Results statistically robust under uncertainty

The results offer empirical evidence for shifting from age-based resurfacing to maintenance planning for highway networks, which is driven by conditions and informed by risk.

- Model Validation and Comparative Benchmarking

Validation was performed using independent field data (2021-2024) not used for model calibration.

  - Deterioration Model Validation

The parameters considered for validation included:

- 64 homogeneous sections

- Three-year panel observations

- Observed parameters: IRI, rut depth, cracking, deflection

Table 8: Statistical Indicators of Model Validation

| Metric | Value | Interpretation |
| --- | --- | --- |
| R² | 0.81 | Strong explanatory power |
| RMSE | 0.42 m/km | Acceptable prediction error |
| MAPE | 9.6% | Within practical PMS tolerance |
| Durbin-Watson | 1.94 | No autocorrelation |

The model demonstrated a statistically significant explanatory capability (p < 0.01). The residuals were normally distributed, satisfying the regression assumptions.

  - Logistic Failure Model Validation

The probability-of-failure model was validated using the observed structural intervention data.

Pfailure=11+e-(-5.64+0.93IRI+2.11D)

Table 9: Indicators of suitability of logistic modelling for structural risk estimation

| Indicator | Value |
| --- | --- |
| Accuracy | 87% |
| Sensitivity | 0.84 |
| Specificity | 0.89 |
| AUC (ROC) | 0.91 |

The Area Under Curve (AUC = 0.91) indicates excellent discriminatory power.

  - Lifecycle Cost Model Verification

Lifecycle cost outputs were cross validated using:

- Tamil Nadu Schedule of Rates (2023–24)

- Historical PWD maintenance records (2017–2023)

Table 10: Calculated Error Margin in Cost Projection

| Cost Component | Deviation from Observed |
| --- | --- |
| Overlay | +4.8% |
| Preventive Treatment | −3.2% |
| Structural Strengthening | +6.1% |

The mean absolute cost deviation was 4.7%. This falls within the acceptable uncertainty bounds for infrastructure lifecycle modelling.

  - Comparative Benchmarking Against Conventional Practice

Benchmark references aligned with periodic resurfacing practices followed by State Highway agencies generally adhere to the following:

- 5-year overlay cycle

- No explicit structural trigger

- Budget-first prioritization

Table 11: Performance Benchmark Results

| Indicator | Periodic Strategy | Optimized Strategy |
| --- | --- | --- |
| Lifecycle Cost | ₹248 Cr | ₹202 Cr |
| Structural Distress (Year 2045) | 22% | 8% |
| Mean IRI | 3.9 m/km | 3.3 m/km |
| Budget Volatility Index | 0.62 | 0.28 |

The optimized framework improves both the economic and engineering performance metrics.

  - Sensitivity to Key Parameters

A deterministic sensitivity analysis was performed by varying the following parameters:

- Traffic growth (±20%)

- Rainfall intensity (±15%)

- Discount rate (8–12%)

The key Observations are as follows:

- Traffic growth has the greatest influence on the lifecycle cost.

- Rainfall significantly affects the deterioration slope.

- The discount rate moderately influences the economic ranking but does not alter the strategy’s superiority.

  - Robustness Under Budget Stress

Under a constrained annual budget scenario (−20% allocation):

- A periodic strategy leads to a rapid backlog accumulation.

- The optimized strategy reprioritizes high-risk freight segments.

- Structural distress was limited to 15% vs. 31% under the periodic approach.

This demonstrates the resilience of the proposed framework.

  - Discussion

The validation results confirmed that:

- The deterioration model satisfies the statistical adequacy criteria.

- Failure probability modelling is reliable for structural decision-making.

- Lifecycle projections are closely aligned with real cost structures.

- Risk-weighted prioritization is more effective than time-based resurfacing in both normal and limited-budget scenarios.

The framework is compatible with the current PMS structures utilized by Indian State Highway agencies and can be incorporated without fundamentally changing data collection practices.

- Policy Implications and Implementation Framework for Indian Highway Agencies

References

  - Rationale for Policy Transition

Indian highway agencies, particularly State Public Works Departments (PWDs) and agencies operating under the Ministry of Road Transport and Highways (MoRTH), traditionally adopt periodic resurfacing cycles (typically 5-6 years) for flexible pavements. While administratively convenient, this approach has the following drawbacks:

- Fails to incorporate structural capacity indicators directly

- Leads to premature overlays on low-risk sections

- Delays strengthening of structurally vulnerable stretches

- Produces cyclical budget spikes

This study shows that a condition-triggered, risk-weighted lifecycle framework provides economic and engineering advantages. Therefore, a gradual shift toward performance-based maintenance planning is justified.

  - Strategic Policy Implications

    - Shift from Time-Based to Threshold-Based Intervention

Agencies should institutionalize trigger thresholds based on the following:

- IRI (functional threshold),

- Rut depth (surface deformation threshold),

- Characteristic deflection (structural threshold).

This approach bases maintenance decisions on the actual condition of the pavement rather than on time.

    - Integration of Structural Evaluation in PMS

Although deflection testing is typically performed during overlay design, it should be integrated into routine Pavement Management System (PMS) decision workflows.

Recommended actions:

- Mandatory deflection testing for sections exceeding IRI 3.5 m/km.

- Creation of a structural health index combining deflection and cumulative ESAL.

- Integration of structural triggers into annual maintenance prioritization lists.

    - Risk-Based Budget Allocation

Instead of uniform resurfacing allocation, annual maintenance budgets should be prioritized using the following:

Risk=Pfailure×Traffic×Freight×StrategicImportance

High-freight corridors and industrial access roads should be prioritized, even if the surface indicators appear moderate. This improves the network-level economic productivity.

    - Lifecycle-Based Budgeting

The adoption of multi-year rolling lifecycle budgeting (5-10 years) is recommended to:

- Smooth expenditure patterns

- Reduce fiscal volatility

- Improve contractor engagement planning

- Enhance transparency in public expenditure

  - Implementation Framework for State Highway Agencies

A phased implementation model is recommended to ensure practical feasibility (Table 12).

Table 12: Implementation Framework for Adoption of Condition-Triggered and Risk-Weighted Pavement Management by Indian State Highway Agencies

| Phase | Implementation Stage | Primary Objectives | Key Activities | Institutional Requirements |
| --- | --- | --- | --- | --- |
| Phase I | Institutional Preparation (Year 1) | Establish policy foundation for performance-based maintenance | • Issue policy notification adopting condition-triggered planning • Define functional and structural intervention thresholds • Develop data collection standards • Capacity building of PMS engineers | • State-level PMS coordination cell • Training programs for field engineers • Standardized survey protocols |
| Phase II | Pilot Corridor Implementation (Years 2–3) | Demonstrate operational feasibility through pilot validation | • Select representative high-traffic corridors • Conduct detailed condition and deflection surveys • Apply lifecycle cost modelling • Compare periodic vs optimized strategies | • Dedicated technical evaluation team • Analytical software support • Third-party technical review |
| Phase III | Network-Level Scaling (Years 4–6) | Expand optimized maintenance planning across entire State Highway network | • Integrate optimization module into PMS software • Statewide segmentation and risk scoring • Annual dynamic prioritization based on risk index | • Centralized data management system • State PMS analytics unit • Periodic calibration mechanism |
| Phase IV | Institutionalization and Continuous Improvement (Beyond Year 6) | Transition toward mature asset management practice | • Continuous deterioration model calibration • Integration with GIS decision platforms • Climate resilience assessment • Independent performance audit | • Dedicated pavement asset management division • Academic and research partnerships • Digital decision dashboards |

  - Data Requirements and Infrastructure

To operationalize the framework, the data required by the agencies are listed in Table 13.

Table 13: Supporting Data and Monitoring Requirements for Implementation

| Data Category | Purpose in Framework | Recommended Frequency | Implementation Remarks |
| --- | --- | --- | --- |
| Roughness (IRI) Survey | Functional performance monitoring | Annual | Vehicle-mounted profilers preferred |
| Distress Mapping | Preventive treatment triggering | Annual | Automated survey desirable |
| Deflection Testing | Structural capacity evaluation | Every 3–5 years | Mandatory before overlay decision |
| Traffic Volume & Classification | Risk weighting and ESAL estimation | Continuous / Annual | Use WIM stations where feasible |
| Climatic Data (Rainfall/Temperature) | Deterioration calibration | Annual | Integrate with IMD datasets |
| Maintenance History Database | Lifecycle modelling | Continuous | Essential for calibration refinement |

  - Financial and Economic Impact

Projected statewide benefits (extrapolated from the case study findings):

- 15-20% lifecycle cost reduction

- 20-30% improvement in serviceable network length

- Reduced emergency rehabilitation expenditure

- Improved freight corridor reliability

For large states with 10,000-15,000 km of State Highway networks, savings may translate into hundreds of crores over a 20-year horizon.

  - Administrative and Capacity Considerations

Key enablers:

- Capacity building in data analytics and lifecycle modelling

- Adoption of centralized digital PMS dashboards

- Collaboration with academic institutions for model calibration

- Periodic third-party validation

Barriers may include:

- Resistance to change from established resurfacing cycles

- Limited structural testing equipment availability

- Budget rigidity within annual allocation systems

These can be mitigated through phased rollouts and pilot success demonstrations.

  - Long-Term Vision

A mature implementation pathway could evolve as follows:

- Statewide reliability-based pavement asset management

- Integration with GIS-enabled decision support systems

- Corridor-level freight risk modelling

- Climate-resilient pavement maintenance planning

Ultimately, the transition to condition-triggered and risk-weighted lifecycle optimization aligns Indian highway agencies with international best practices in infrastructure asset management.

- Conclusion

The paper has come up with a condition-based lifecycle optimization model of a two-lane flexible pavement maintenance planning in Indian tropical conditions. The framework is a combination of pavement assessment, deterioration modelling, structural reliability analysis, and life-cycle cost analysis into a single decision-support technique.

A two-lane bituminous State Highway corridor near Chennai was tested in practice and demonstrated obvious benefits over more traditional periodic resurfacing. The optimized plan recorded 18 per cent decrease in discounted life cycle cost and 26 per cent in the state of the serviceable network and a 50-per cent less frequency in structural rehabilitation in a 20-year perspective.

The findings also indicate the significance of the joint consideration of functional indicators and structural assessment in prioritization of maintenance. Risk-based decision logic enhances the stability of the budget and makes it possible to efficiently use the maintenance resources. Sensitivity analysis and statistical validation validated the strength of the model with changes in the traffic growth, climatic and economic aspects.

The proposed methodology can be used in the Indian pavement engineering practices, and it can be adapted to the existing Pavement Management Systems with only slight adjustments. The results justify the switch in time-based policies of resurfacing roads to performance-based lifecycle management of Indian highway networks.

- Future Research

Future research should focus on the following aspects:

- Integration of mechanistic-empirical pavement response models within lifecycle optimization,

- Extension of the framework to network-level multi-corridor optimization,

- Incorporation of climate-resilient deterioration modelling,

- Application within digital and GIS-enabled pavement asset management platforms, and

- Linkage of risk-based prioritization with performance-based maintenance contracting systems.

Further validation across diverse climatic regions and traffic environments in India will strengthen the general applicability and support large-scale implementation by highway agencies.

References

Haas, R., Hudson, W. R., and Zaniewski, J. P. 1994. Modern Pavement Management. Krieger Publishing, Malabar, FL.

Indian Roads Congress (IRC). 2014. IRC:115-2014—Guidelines for Structural Evaluation and Strengthening of Flexible Road Pavements Using Falling Weight Deflectometer. New Delhi, India.

Indian Roads Congress (IRC). 2015. IRC:82-2015—Code of Practice for Maintenance of Bituminous Pavements. New Delhi, India.

Indian Roads Congress (IRC). 2018. IRC:37-2018—Guidelines for the Design of Flexible Pavements. New Delhi, India.

Kerali, H. G. R., Odoki, J. B., and Stannard, E. E. 2000. HDM-4 Highway Development and Management Model. World Bank, Washington, DC.

Ministry of Road Transport and Highways (MoRTH). 2022. Basic Road Statistics of India 2021–22. Government of India, New Delhi.

Paterson, W. D. O. 1987. Road Deterioration and Maintenance Effects: Models for Planning and Management. Johns Hopkins University Press, Baltimore.

Transportation Research Board (TRB). 2010. Asset Management for Transportation Infrastructure Systems. National Academies Press, Washington, DC.

OECD. 2001. Asset Management for the Roads Sector. Organisation for Economic Co-operation and Development, Paris.

Shahin, M. Y. 2005. Pavement Management for Airports, Roads, and Parking Lots. Springer, New York

Uddin, W., Hudson, W. R., and Haas, R. 2013. Public Infrastructure Asset Management. McGraw-Hill, New York.

American Association of State Highway and Transportation Officials (AASHTO). 2011. Transportation Asset Management Guide: A Focus on Implementation. Washington, DC.

Cambridge Systematics. 2006. Risk-Based Transportation Asset Management. NCHRP Report 551, Transportation Research Board, Washington, DC.

Federal Highway Administration (FHWA). 2016. Pavement Preservation: A Road Map for the Future. U.S. Department of Transportation, Washington, DC.

Labi, S., Sinha, K. C., and Fricker, J. D. 2005. “Economic evaluation of highway asset preservation strategies.” Transportation Research Record, 1924, 1–9.

Markow, M. J., and Hyman, W. A. 2009. Bridge and Highway Infrastructure Asset Management. Wiley, Hoboken, NJ.

Odoki, J. B., and Kerali, H. G. R. 2000. HDM-4 Analytical Framework and Model Description. World Bank, Washington, DC.

Prozzi, J. A., and Madanat, S. M. 2000. “Development of pavement performance models by combining experimental and field data.” Journal of Infrastructure Systems, 6(1), 9–22.

Fwa, T. F. 2005. “Network-level pavement management optimization.” Journal of Transportation Engineering, 131(5), 387–395.

Hall, K. T., Correa, C. E., Simpson, A. L., and Van Deusen, D. A. 2003. Life-Cycle Cost Analysis Primer. FHWA, Washington, DC.

Madanat, S., Mishalani, R., and Ibrahim, W. 1995. “Estimation of infrastructure transition probabilities from condition rating data.” Journal of Infrastructure Systems, 1(2), 120–125.

Morcous, G. 2006. “Performance prediction of infrastructure systems using reliability modelling.” Journal of Infrastructure Systems, 12(3), 146–155.

Zhang, Z., and Durango-Cohen, P. 2013. “Dynamic programming optimization for pavement maintenance scheduling.” Transportation Research Part B, 57, 1–19.