Identifying and Mitigating  the Impact of Insecurity on Construction Project Delivery: A Case Study of Kebbi State.

By

Y.S. Abubakar¹, MJ Abubakar¹and G.B. Wurma²

1Quantity Surveying Department, Federal University, Birnin Kebbi, Kebbi State, Nigeria

2Architecture Department, Federal University, Birnin Kebbi, Kebbi State, Nigeria

*Email: yahayaabubakar21@gmail.com

Abstract

The construction sector is crucial for economic growth, yet its efficiency is increasingly jeopardized by insecurity, especially in developing regions. This study examines the effects of insecurity on construction project delivery in Kebbi State, Nigeria, aiming to identify key security challenges and propose effective mitigation strategies. A mixed-method approach was utilized, combining quantitative data from 100 structured questionnaires administered to construction professionals and qualitative insights from 15 semi-structured interviews with stakeholders such as contractors, project managers, and community leaders. The analysis included descriptive statistics, the Relative Importance Index (RII), and regression analysis for quantitative data, while thematic analysis was used for qualitative data. Results indicate that insecurity significantly hampers construction performance, with project delays (Mean = 4.45) and cost overruns (Mean = 4.32) being the most critical impacts. Other significant effects include workforce shortages, decreased productivity, and material theft. The RII results highlight that banditry (0.89), kidnapping (0.85), and theft/vandalism (0.80) are the primary security threats in the area. Regression analysis reveals a strong negative correlation between insecurity and project performance (β = -0.68, p < 0.05), indicating that higher insecurity levels lead to worse project outcomes. Qualitative findings support these results, emphasizing frequent disruptions, increased security costs, worker anxiety, and inadequate government responses. The study concludes that insecurity is a major factor influencing construction project success in Kebbi State, affecting operational efficiency, financial stability, and workforce morale. Recommendations include enhanced security measures, improved government intervention, community engagement, comprehensive risk management, and stronger collaboration among stakeholders.

Keywords

Insecurity, Construction Projects, Cost Overruns, Relative Importance Index, Nigeria

1.0 Introduction

Construction projects are complex and resource-intensive, making them particularly susceptible to disruptions caused by insecurity (Waqas et al., 2019). This vulnerability is heightened in regions with high levels of civil unrest, organized crime, or political instability, where project delays and cost overruns become common due to threats like kidnapping, banditry, and terrorism (Adedokun et al., 2023; Ebekozien et al., 2024). Such security challenges severely impede project timelines and overall performance, creating significant uncertainties regarding project outcomes and financial viability (Ebekozien et al., 2024).

In Kebbi State, located in northwestern Nigeria, escalating insecurity due to cross-border crimes and armed banditry disrupts construction projects, leading to delays, increased costs, reduced workforce availability, and discouragement of local and foreign investments (Shameli-Sendi et al., 2016). The nature of construction work, which relies heavily on human labor and involves valuable equipment, makes it particularly vulnerable to security threats. Consequently, project managers often resort to unplanned contingency measures, adversely affecting overall project performance (Ragu-Nathan et al., 2008; D’Arcy et al., 2014).

Recent studies emphasize that insecurity imposes both direct and indirect costs on construction activities. Direct impacts include material theft, vandalism, and financial losses due to project delays, whereas indirect impacts involve reduced labor productivity, increased stress among workers, and diminished investor confidence (Ezenwobodo & Samuel, 2022; Ahmad et al., 2012). Furthermore, insecurity forces construction firms to allocate resources toward security management instead of focusing on core project objectives, exacerbating cost overruns and compromising project quality.

1.1 Statement of the Problem

Despite recognizing the significance of insecurity on construction projects, there is a lack of localized research specifically investigating its effects in Kebbi State. While national studies highlight general trends, they often overlook the unique socio-cultural, geographic, and security dynamics of the northwestern region. Consequently, project managers and policymakers lack evidence-based strategies to effectively mitigate insecurity-related risks, leading to frequent delays, cost escalations, and reduced productivity, which undermine the sector's contribution to regional development and national growth.

1.2 Aim and Objectives of the Study

The primary aim of this study is to identify and mitigate the impact of insecurity on construction projects in Kebbi State. Specific objectives include:

- Identifying the key security risks affecting construction projects in Kebbi State.

- Evaluating the impact of these risks on project timelines, costs, and workforce productivity.

- Developing  strategies for mitigating insecurity-related risks in construction projects.

1.3 Research Questions

This study seeks to answer the following questions:

- What are the predominant forms of insecurity affecting construction projects in Kebbi State?

- How does insecurity influence the cost, duration, and quality of construction projects?

- What  strategies  can be developed to mitigate security related risks in the construction projects

1.4 Significance of the Study

This research is significant for several reasons. Firstly, it provides evidence-based insights into the nature and extent of insecurity in Kebbi State’s construction sector, which can inform policymakers and security agencies. Secondly, the findings offer practical strategies for project managers to mitigate insecurity risks, optimize resource allocation, and improve project outcomes. Finally, the study contributes to the academic literature on construction risk management, particularly in regions affected by insecurity, serving as a reference for future research in similar socio-political contexts (Ahmad et al., 2012; Webb et al., 2014; Shameli-Sendi et al., 2016).

1.5 Scope of the Study

This study focuses on construction projects in Kebbi State, particularly those most affected by insecurity, including roadworks, commercial buildings, and public infrastructure projects. A mixed-method approach was adopted, combining quantitative data from questionnaires administered to construction professionals with qualitative data from interviews with key stakeholders, including project managers, contractors, and community leaders.

2.0 Literature Review

2.1 Concept of Insecurity in Nigeria

Insecurity refers to situations of exposure to threats and violence, often resulting in economic or social disruption. In Nigeria, it manifests through banditry, terrorism, kidnapping, communal clashes, and theft, with northern states disproportionately affected (Ahmad, Hadgkiss, & Ruighaver, 2012; Webb et al., 2014). These threats create an environment of uncertainty and elevate operational risks for construction projects, especially in remote or conflict-prone areas (Shameli-Sendi et al., 2016).

2.2 Forms of Insecurity Affecting Construction Projects

Several forms of insecurity impact construction activities:

    - Banditry and Armed Attacks: Frequent armed raids disrupt construction schedules and threaten workforce safety (Ezenwobodo & Samuel, 2022).

    - Kidnapping and Ransom Threats: Workers may be abducted for ransom, leading to labor shortages and psychological stress (Shameli-Sendi et al., 2016).

    - Theft and Vandalism: Equipment and materials are often stolen or damaged, resulting in financial losses (Ragu-Nathan et al., 2008).

    - Communal Conflicts: Land disputes and inter-communal clashes create uncertainties around project sites, causing suspensions or delays (D’Arcy, Hovav, & Galletta, 2014).

These forms of insecurity compromise both operational efficiency and the financial sustainability of projects.

2.3 Theoretical Framework

This study is grounded in Risk Management Theory, which posits that project outcomes are significantly influenced by the identification, assessment, and mitigation of risks (Ragu-Nathan et al., 2008). In the context of insecurity, risks can be external (banditry, communal clashes) or internal (organizational preparedness, workforce readiness). Integrating both quantitative and qualitative insights provides a comprehensive understanding of these risks.

3.0 Methodology

3.1 Research Design

The study employs a mixed-method research design, combining quantitative and qualitative approaches:

- Quantitative Approach: Structured questionnaires were administered to construction professionals, including project managers, engineers, contractors, and site supervisors. This approach enabled the measurement of insecurity impacts using numerical scales (Likert scale 1–5) and statistical analysis.

- Qualitative Approach: Semi-structured interviews were conducted with stakeholders, including contractors, community leaders, and local security personnel. This approach provided deeper insights into lived experiences, contextual factors, and mitigation strategies not captured through surveys.

The convergent parallel design was adopted, allowing for concurrent collection of quantitative and qualitative data, which were integrated during analysis to provide a comprehensive understanding of insecurity’s impact.

3.2 Study Area

The focus of the study is Kebbi State, located in northwestern Nigeria, which has experienced increasing security challenges such as armed banditry, kidnapping, communal clashes, and theft, particularly in areas with ongoing construction projects. The study targeted urban and semi-urban locations with active roadworks, commercial buildings, and public infrastructure projects, where insecurity has tangible impacts on construction activities.

3.3 Population of the Study

The study population includes:

Construction Professionals: Engineers, quantity surveyors, contractors, project managers, and site supervisors operating in Kebbi State.

Key Stakeholders: Community leaders, security personnel, and project sponsors knowledgeable about local insecurity and project execution.

3.4 Sampling Technique and Sample Size

A purposive sampling technique was employed to select respondents who have direct experience with construction projects affected by insecurity. This technique ensures that participants are knowledgeable and can provide reliable information.

Quantitative Sample: 100 respondents completed structured questionnaires.

Qualitative Sample: 15 stakeholders participated in semi-structured interviews.

This sample size aligns with similar studies in construction risk management, providing adequate data for both statistical and thematic analyses.

3.5 Research Instruments

Questionnaire: The questionnaire consisted of three sections:

Section A: Demographics – Age, gender, role, years of experience.

Section B: Insecurity Factors – Likert-scale items measuring exposure to insecurity, types of threats, and frequency.

Section C: Project Impact – Likert-scale items assessing project delays, cost overruns, workforce productivity, material loss, and mitigation measures.

The questionnaire was validated through a pilot study with 10 respondents, achieving a Cronbach’s alpha of 0.86, indicating high internal consistency.

Semi-Structured Interview Guide: The interview guide included open-ended questions on: Experiences of insecurity on construction projects, perceived causes and patterns of insecurity, effectiveness of current mitigation strategies and suggestions for improving project resilience. Interviews were recorded (with consent) and transcribed for thematic analysis.

3.6 Ethical Considerations

Permissions were obtained from relevant authorities and organizations. Questionnaires were distributed in person and via email where applicable. Face-to-face interviews were conducted with stakeholders in secure locations, lasting 30–45 minutes. Quantitative data were coded and analyzed using SPSS, while qualitative data were transcribed and organized in NVivo.

3.7 Data Analysis

3.7.1 Quantitative Analysis:

Descriptive Statistics: Employed to find frequencies, percentages, mean scores, and standard deviations.

Relative Importance Index (RII): Used to rank the severity of insecurity impacts as perceived by respondents.

Regression Analysis: Assessed the relationship between insecurity and project performance.

Hypotheses Testing:

Null hypothesis (H0): Insecurity has no significant effect on project performance.

Alternative hypothesis (H1): Insecurity significantly affects project performance.

3.7.2 Qualitative Analysis:

Thematic Analysis: Transcripts were coded, and recurring patterns were grouped into themes.

Triangulation: Qualitative insights were integrated with quantitative findings to validate results and provide context.

3.7.3 Validity and Reliability: Instruments were validated by academic experts, and pilot testing ensured content relevance, where Cronbach’s alpha > 0.8 which indicates strong internal consistency for the survey instrument. Triangulation was employed in combining quantitative and qualitative data which enhances reliability and reduces bias.

4.0 Results and Discussion

4.1 Introduction

This section presents the analysis of data collected from respondents and discusses findings in detail. The results are analyzed using descriptive statistics (mean scores), Relative Importance Index (RII), and regression analysis, interpreted in line with the research objectives and existing literature. Qualitative results are also discussed.

4.2 Demographic Characteristics of Respondents

The respondents included engineers, quantity surveyors, contractors, and site supervisors with varying years of experience. Most had over five years of experience, indicating that the data obtained is reliable and based on practical industry knowledge.

4.3 Analysis of the Impact of Insecurity on Construction Projects

| Table 4.1: Mean Score Analysis of Impact of Insecurity |  |  |
| --- | --- | --- |
| Impact Factor | Mean Score | Rank |
| Project delays | 4.45 | 1 |
| Cost overruns | 4.32 | 2 |
| Workforce shortage | 4.1 | 3 |
| Reduced productivity | 4.05 | 4 |
| Material theft/loss | 3.98 | 5 |
| Field Survey, 2026 |  |  |

The results indicate that project delays (Mean = 4.45) are the most significant impact of insecurity on construction projects in Kebbi State. This suggests that insecurity frequently disrupts work schedules, causing temporary site shutdowns and limiting access to project locations. Cost overruns (Mean = 4.32) rank second, reflecting the financial burden imposed by insecurity, which arises from hiring security personnel, replacing stolen materials, and compensating for project delays.

Workforce shortage (Mean = 4.10) indicates that insecurity discourages skilled workers from accepting or continuing jobs in high-risk areas. Reduced productivity (Mean = 4.05) suggests that even when workers remain on-site, their efficiency is compromised due to fear and psychological stress. Finally, material theft/loss (Mean = 3.98) remains a critical issue, contributing to financial losses and disrupting workflow continuity. Overall, the high mean scores indicate that insecurity has a significant and widespread impact on construction project performance.

4.4 Major Forms of Insecurity

| Table 4.2: Relative Importance Index (RII) of Insecurity Factors |  |  |
| --- | --- | --- |
| Insecurity Factor | RII | Rank |
| Banditry | 0.89 | 1 |
| Kidnapping | 0.85 | 2 |
| Theft/Vandalism | 0.8 | 3 |
| Field Survey, 2026 |  |  |

Results show that banditry (RII = 0.89) is the most significant form of insecurity affecting construction projects in Kebbi State. Kidnapping (RII = 0.85) ranks second, highlighting the risk faced by construction workers. Theft and vandalism (RII = 0.80) remain significant threats, leading to material loss and additional costs. The high RII values indicate that all identified insecurity factors are highly significant, confirming that insecurity is a major challenge in the study area.

4.5 Regression Result

| Table 4.3: Regression Results |  |  |  |
| --- | --- | --- | --- |
| Variable | Coefficient (β) | t-value | p-value |
| Constant | 1.25 | 2.1 | 0.038 |
| Insecurity (INS) | -0.68 | -5.42 | 0.000 |
| Field Survey, 2026 |  |  |  |

R² = 0.62

The regression results indicate that insecurity has a statistically significant negative effect on construction project performance. The coefficient for insecurity (β = -0.68) suggests that a unit increase in insecurity leads to a 68% decrease in project performance, holding other factors constant. The p-value (0.000 < 0.05) confirms that this relationship is statistically significant, and the R² value of 0.62 implies that approximately 62% of the variation in project performance can be explained by insecurity. This provides strong empirical evidence that insecurity is a key determinant of project outcomes in Kebbi State.

4.6 Qualitative Interview Results

In addition to quantitative data obtained through questionnaires, qualitative data were collected through semi-structured interviews with selected stakeholders, including project managers, contractors, site engineers, and local community representatives. This approach provided deeper insights into how insecurity affects construction projects beyond numerical analysis.

4.6.1 Key Themes from Interviews

- Disruption of Construction Activities: Most respondents emphasized that insecurity frequently leads to temporary or complete shutdowns of project sites. “There are times we have to suspend work for weeks due to security threats in the area,” noted a project manager.

- Increased Project Cost Due to Security Measures: Interviewees highlighted the financial burden of insecurity, particularly regarding security arrangements. “We spend a lot on hiring local vigilantes and sometimes even security escorts for materials,” stated a contractor.

- Fear and Workforce Challenges: A recurring issue was the reluctance of workers to operate in high-risk areas. “Some skilled workers refuse to come to site once they hear about attacks nearby,” reported a site engineer.

- Community Relations as a Security Strategy: Some respondents emphasized the importance of engaging local communities as a means of protection. “When the community supports the project, security improves because they help monitor activities,” noted a contractor.

- Ineffectiveness of Government Security Response: Many stakeholders expressed dissatisfaction with the level of government intervention. “Government security presence is not enough to guarantee safety on sites,” remarked a project supervisor.

4.7 Integration of Quantitative and Qualitative Findings

| Table 4.4 Integration of Quantitative and Qualitative Findings |  |
| --- | --- |
| Quantitative Finding | Qualitative Insight |
| Project delays ranked 1st | Site shutdowns and work suspension confirmed |
| Cost overruns ranked 2nd | Extra spending on security explained |
| Workforce shortage | Fear and refusal to work identified |
| Field Survey, 2026 |  |

The qualitative data reveals that insecurity is not only a measurable risk but also a lived experience for stakeholders. It affects decision-making, planning, and execution of construction projects. Findings suggest that insecurity introduces uncertainty and unpredictability, compelling contractors to engage in reactive planning and creating psychological burdens for workers.

5.0 Conclusion and Recommendations

5.1 Conclusion

This study investigated the impact of insecurity on construction projects in Kebbi State, Nigeria, using a mixed-method approach that combined quantitative surveys with qualitative interviews. Findings reveal that insecurity significantly affects construction projects in various dimensions:

Operational Impact: Project delays were identified as the most critical consequence of insecurity, with frequent banditry and theft disrupting site operations.

Financial Impact: Cost overruns were observed as a major challenge, largely due to expenses on security personnel, insurance premiums, and project downtime.

Human Resource Impact: Workforce shortages and reduced productivity were highlighted, as workers are often reluctant to operate in high-risk areas.

Investor Confidence: The prevalence of insecurity discourages investments and contractor engagement in vulnerable regions, further affecting sector growth.

Overall, the study concludes that insecurity is a major determinant of construction project performance in Kebbi State. The integration of both quantitative and qualitative data underscores that addressing insecurity requires a multi-faceted approach involving government, communities, and private sector stakeholders.

5.2 Recommendations

Based on the findings, the following strategies are proposed to mitigate the impact of insecurity on construction projects:

Enhanced Security Measures: Construction firms should invest in advanced security solutions, including surveillance systems and trained private security personnel for high-risk sites.

Government Intervention: Strengthen security presence around construction zones through coordination with local authorities and rapid response policies.

Community Engagement: Foster collaboration with local leaders to enhance project safety and gain support for security initiatives.

Risk Management Planning: Incorporate comprehensive security risk assessments during project planning and establish contingency plans for potential disruptions.

Insurance Policies: Adopt comprehensive insurance covering workers, equipment, and materials to mitigate financial losses from insecurity-related incidents.

Workforce Training and Awareness: Conduct safety training sessions for workers to enhance preparedness for potential security incidents.

Stakeholder Collaboration: Encourage collaboration between contractors, investors, and government agencies to share security intelligence and best practices.

Policy and Legislative Support: Advocate for regional policies aimed at reducing insecurity, including rehabilitation programs for offenders and conflict mediation.

References

Adedokun, O. A., Ajayi, O. M., & Adebayo, T. A. (2023). Impact of Insecurity on Construction Project Performance in Nigeria. Journal of Engineering, Design and Technology, 21(4), 1023–1041.

Ahmad, A., Hadgkiss, J., & Ruighaver, A. B. (2012). Continuous Improvement in Information Security Risk Management: An Empirical Study. Journal of Information Security Research, 7(3), 45–61.

Ahmadzai, S., & Ye, G. (2024). Security Risks and their Impact on Construction Project Delivery in Conflict-Prone Regions. Journal of Construction in Developing Countries, 29(1), 85–102.

Aigbavboa, C., Thwala, W., & Akinradewo, O. (2025). Organized Crime and Infrastructure Project Delivery in Developing Economies. International Journal of Construction Management, 25(2), 215–228.

D’Arcy, J., Hovav, A., & Galletta, D. (2014). User Awareness of Security Countermeasures: A Study of Organizational Information Security. Computers & Security, 43, 45–56.

Dladla, S., Moyo, T., & Mhlongo, N. (2025). Construction Project Risks in Conflict Zones: Evidence from Developing Countries. Built Environment Project and Asset Management, 15(1), 66–82.

Ebekozien, A., Aigbavboa, C., & Thwala, W. (2024). Insecurity and Project Delivery Challenges in Construction Industries. Journal of Construction Project Management and Innovation, 14(2), 134–150.

Ezenwobodo, P., & Samuel, S. (2022). Use of Mathematical Software Packages in Teaching and Learning: Evidence from Nigerian Colleges of Education. International Journal of Research Publication and Reviews, 13(2), 55–72.

Onunwa, A. (2025). Insecurity and Economic Development in Nigeria. Lagos: Academic Press Nigeria.

Oyibokure, K., & Okolie, D. (2023). Security Challenges and Development in Africa. Abuja: African Policy Research Institute.

Ragu-Nathan, T., Tarafdar, M., Ragu-Nathan, B., & Tu, Q. (2008). The Consequences of Technostress for End Users in Organizations. Information Systems Research, 19(4), 417–433.

Shameli-Sendi, A., Aghababaei-Barzegar, R., & Cheriet, M. (2016). Taxonomy of Information Security Risk Assessment (ISRA). Computers & Security, 57, 14–30.

Shameli-Sendi, A., Dehghantanha, A., & Choo, K. K. R. (2016). Information Security Risk Management: A Review. Journal of Information Security, 7(3), 165–180.

Waqas, M., Butt, A. A., & Khan, M. (2019). Impact of Security Risks on Construction Project Performance. International Journal of Construction Engineering and Management, 8(2), 45–52.

Webb, H., Ahmad, A., Maynard, S. B., & Shanks, G. (2014). A situation awareness model for information security risk management. Information & Management, 51(5), 498–510.

Webb, H., Ahmad, A., Maynard, S., & Shanks, G. (2014). The Human Factor in Information Security Risk Management. Information & Management, 51(5), 498–508.